## QA Pathway
Title of Phase | Description of the Phase | Gate | Actions - Relationship Manager | Actions - Designer | Actions - Developer | Deliverable (At the end of the Phase / stage) | Definition of Done Criteria | What good looks like | Definition of Done Statement | Part of the process | What good looks like | Outcomes - | Go / No Go Decision (QA)
The Base Building Relationships WIP | Commissioning Work |  | 🔸 Building (Commissioning work) - relationship building that lead to projects coming into the Lab workflow 🔸 Hold - Holding the relationships throughout the duration of interaction with the Lab. 🔸 Expectation management on what the lab is and isn’t - eg that it’s R&D focused 🔸 Manage expectation that the work will be prioritised with others 🔸 Identify what work to engage to utilise available capacity and skills in the lab team 🔸 Allocating a person from the lab team to hold the relationship 🔸 Workshops 🔸 Meetings |  |  | 🔹 Authorisation to undertake scoping work in a particular area |  |  | ✅ Reliability of research team ✅ The right people are sourced ✅ Clear understanding MOU |  |  |  | https://drive.google.com/open?id=1iU5lSHXhfWhhuJbAxaBT4v4-MGoLlmxG536WeJhS1PU
Scoping WIP | Assessment scoping determines suitability of work for the lab approach and goals. A recommendation is made on whether more time should be spent working with stakeholders to project scope the work or if an alternative path is more suitable and what support they need to pursue it. Formula for Measurements: Alignment and Level of Confidence | Gate 1 Assessment Scoping | 🔸 Answer questions: 2.) Does the Lab team and it’s process add value to this project? Could the team use a vendor or in-house service design team instead? 3.) Where does the Lab workflow process fit in? E.g. Research Discovery or Build (Alpha) 🔸 Complete the recommended scoping questions - DEFINE 🔸 Workshops - Run a short workshop or investigation conversation (Scoping session) 🔸 Meetings - Meet with said team and leaders. 🔸 Identify resources required 🔸 Identify if the projects fits within the labs vision and goals 🔸 Identity if the work is a: 1.) Requst or 2.) A work programme item or 3.) A lab work agenda 🔸 Prioritise work for project scoping and allocate persons to do the scoping - strategy, relationship, design, dev. 🔸 Meeting with SIRG member / initial contact re scopping session(s) 🔸 Process lead creates design project scoping brief as part of recommendations paper 🔸 Process lead describes scoping outcomes as part of recommendations paper for sponsor, SIRG and lab leadership. |  |  | One-pager description of the project and recommended next steps | Explanation on how this work is suitable for the lab to investigate further. Stakeholders understand our service offering and approach | Identified work we should and shouldn't be doing (see values and goals of lab e.g. cross govt) | Trello card updated and shifted to project scoping for follow up OR referred to more appropriate partner | This is an Action - Validate the project scope in relation to assumptions. | Traceable origin of work and associated pressures (e.g. my boss wants this) Identified product owner/sponsor/lead agency | Managing expectations of Lab and external teams commitment and responsibilities | TBC Reference Questions: Location: D:\Google Drive\LabPlus\Service Design\Operational Workflow\Deliverables_and_WhatGoodLooksLike\Go_and_NoGo_Decision\02 Research Discovery Gate 3 Research Discovery.gdoc https://docs.google.com/open?id=1Gr_KemYEi26l3dtj4yjhyYw4dnGNoYUhantRMPB9p0g Gate 3 Research Discovery_Refining.gdoc https://docs.google.com/open?id=1mFxDH4lUZB2tSBYhNE04-If29MFfPYoORrWRoXIbw_M Gate 5 Project Roadmap.gdoc https://docs.google.com/open?id=157p-nlpgfwTMsNJpFmG-KQfchX_P2os3ekO1taPrlLk
Scoping WIP | Project scoping determines the size, phase, timing and needs for the work to be completed. Formula for Measurements: Sizing and Level of Confidence | Gate 2 Project Scoping | 1.) Are the team / agency / interested-party ready and able to engage/commit with the Lab and its processes? 🔸 Embed with team and leaders. 🔸 Run further session to draft a project scope outline document. 🔸 Discovery research plan/brief 🔸 Resource requirements 🔸 Indicative timeline 🔸 Communicate how we scope their work 🔸 Manage expectations with lead in times, the amount of time to do the work, the approach (ie an in lab agency team working with the lab team or agency support as required), skill gaps need to do the work. 🔸 Identify a sponsor and a product owner for the work. This includes a SIRG member to represent the work too. 🔸 Manage expectation that the work may not be done in the lab - we may use a trusted vendor who aligns with our goals to do the work. We’ll support them with their interaction with the vendor however so we’ll manage that relationship too. 🔸 Constant discussion with sponsors to advise timeframes, resource needs and information required. 🔸 Organise kick off meetings - this includes at the start of the work but also at the start of major stage gates too. 🔸 Arranging coaching sessions if required to lift the capability of people who will be working with the lab team eg design thinking 101. 🔸 Process lead creates scoping outcomes as part of recommendations paper for sponsor, SIRG and lab leadership 🔸 Process lead describes scoping outcomes as part of recommendations paper for sponsor, SIRG and lab leadership. |  |  | 🔹 A project scope document. Suggests the scope of the undertaking and the key areas of focus, includes the scoping outcomes of: - Discovery research plan/brief - Resource requirements - Indicative timeline - Reasons why initiative does not proceed if that decision is made. 🔹 Inception deck and lean canvas for project scoping work | A project brief is created, resources identified and SWIG notified for prioritisation? | Clearly defined scope. Adequate time, expertise and other resources secured | A project brief is created | This is an Action - Validate the project scope in relation to assumptions. | Stakeholders expectations set (approach+deliverables) Risks, constraints and pressures detailed We have an agreed understanding of the job to be done We have an agreed understanding of the success criteria SWIG agree to work? has this already happened? | A deeper understanding of the work and commitment required for completion. - Everyone is comfortable with the work, what it is for, goals/success factors, the approach to be used, the frame to begin with, and an agreement to move forward or cease at this time. So: ¦ Collective agreement/buy-in ¦ Visibility of work ¦ External understanding of Lab service offering ¦ Set of recommendations for the agency and the lab.✅ Clear Understanding & Agreement | TBC Reference Questions: Location: D:\Google Drive\LabPlus\Service Design\Operational Workflow\Deliverables_and_WhatGoodLooksLike\Go_and_NoGo_Decision\02 Research Discovery Gate 3 Research Discovery.gdoc https://docs.google.com/open?id=1Gr_KemYEi26l3dtj4yjhyYw4dnGNoYUhantRMPB9p0g Gate 3 Research Discovery_Refining.gdoc https://docs.google.com/open?id=1mFxDH4lUZB2tSBYhNE04-If29MFfPYoORrWRoXIbw_M Gate 5 Project Roadmap.gdoc https://docs.google.com/open?id=157p-nlpgfwTMsNJpFmG-KQfchX_P2os3ekO1taPrlLk
Research Discovery | A research discovery investigates a complex or open issue. It seeks to establish actionable insights through evidence gathering. It embeds evidential design rigour, and applies quantitative and qualitative methodologies. It generates an understanding of issues and refines complexities into actionable insights Formula for Measurements: Unknown to Known and Level of Confidence | Gate 3 Research Investigation | Capability uplift of an external team (where applicable) 🔸 Manage expectations of what this phase delivers ie broad and shallow research in the area of interest 🔸 Understand if the path forward is within the remit of the lab and its vision and goals 🔸 Update SIRG and SWIG to ensure mandate is kept - - - - - - - - - - - - 🔸 Manage expectations of what this phase delivers ie narrow and deep dive research into a specific issue eg what is the problem, who is experiencing it, when is it happening. 🔸 Understand if the path forward is within the remit of the lab and its vision and goals 🔸 Update SIRG and SWIG to ensure mandate is kept | 🔸 In-depth quantative and qualitative research and evidence into the subject matter 🔸 Co-design, collaboration and outreach. 🔸 Embed evidential design rigour 🔸 Workshops 🔸 Meetings 🔸 Field research 🔸 Audience/stakeholder mapping 🔸 High level Journey mapping 🔸 Current state service analysis 🔸 Ecosystem map 🔸 Market and trend research 🔸 Literature review 🔸 Desk research 🔸 Gap analysis 🔸 Designing research tools 🔸 Gather and share information 🔸 Testing with specialists? 🔸 Analysis/synthesis of research findings 🔸 Identify assumptions 🔸 Prioritisation 🔸 Identify constraints - - - - - - - - - - - - 🔸 Workshops 🔸 Meetings 🔸 Market analysis 🔸 User stories, Archetypes, personas 🔸 Deep dive research 🔸 Blueprints 🔸 Cause analysis 🔸 Reframe problems 🔸 Taxonomies 🔸 Value proposition 🔸 Analytics (data crunching) 🔸 Experiment design/planning 🔸 Hypothesis development 🔸 Analysis/synthesis of research findings 🔸 Surveys (baseline) 🔸 Roleplay 🔸 Scenario building 🔸 Service blueprint 🔸 Surveys 🔸 User testing 🔸 Co-design workshops 🔸 SWOT analysis (decision matrix) 🔸 Options analysis 🔸 Moodboards 🔸 Testing competitors 🔸 Logic flows 🔸 Technical constraints |  | Insights report - Answers the Project Scoping delivery is a research brief | 1) A high level ideal future state has been described (and users subscribe to this vision). | - Defined How might we/design challenges x3 - Validated assumptions - Interim assessment / analysis of data - Topics of interests identified. - A BlueSky state has been described - Is it Feasible / Desirable? | complete when we are confident that... - the research investigation stage has identified and documented one or more actionable insights, that can be explored in a Design Discovery. and - we are confident that we now HAVE to begin design tests to make progress | This is an Action - Validate the project scope in relation to assumptions. | How many research methods applied (eg. desktop, let review, interviews, observation) Experience of researchers | Insights into pain points and opportunities for further research. | TBC Reference Questions: Location: D:\Google Drive\LabPlus\Service Design\Operational Workflow\Deliverables_and_WhatGoodLooksLike\Go_and_NoGo_Decision\02 Research Discovery Gate 3 Research Discovery.gdoc https://docs.google.com/open?id=1Gr_KemYEi26l3dtj4yjhyYw4dnGNoYUhantRMPB9p0g Gate 3 Research Discovery_Refining.gdoc https://docs.google.com/open?id=1mFxDH4lUZB2tSBYhNE04-If29MFfPYoORrWRoXIbw_M Gate 5 Project Roadmap.gdoc https://docs.google.com/open?id=157p-nlpgfwTMsNJpFmG-KQfchX_P2os3ekO1taPrlLk
[6 empty] | 🔹 Information published describing the outcomes and next steps of the work along with a blog post. Likely to include: - Areas for further research Potential audiences - Assumption validation - Stories - Maps - Data - qual/quant -Trends/market including existing players | 2) There is a clear description of who we would design a prototype for. | - Persons of interests identified x4 - Surface pain points - detailed user experiences / sytems processes documented - Archtypes and Motivations - Insights formed and evidenced - detailed user experiences / sytems processes documented - Identification of key user experiences and systems processes to map indepth - Quality documentation (Transcripts, bibliography, audio, video, photos) |  | - Identifying and choosing opportunities to deep dive. |  | Options for ways forward Clarity on what and who needs to be involved next Validation on what they know vs don't (assumptions validated)
[6 empty] | 🔹 Demonstration (ie could be a presentation, report) that likely describes: - A shareable synthesis of the primary and secondary research done - A story that describes the scope and definition of backlog of the opportunities/problems identified - The causal factors - The hypothesis and assumptions that have been validated or eliminated during the work - Specific problem/discrete problem defined - Concise and well evidenced insights - The value the team is targeting with its recommendation on what should be done next and what are the key measures for success/impact - Key measures for success/impact - Multiple "help me's..." | 3) The problems are clearly described that we need to address . | - Problem context is well understood barriers/enablers (determinants) x3 - Insights formed and evidenced - New understanding/knowledge learnt - Topics of interests identified. - Valididated assumptions - Interim assessment / analysis of data - Defined How might we's/design challenges - Surface pain points - Quality documentation (Transcripts, bibliography, audio, video, photos) - detailed user experiences / sytems processes documented |  | - desing inspriation and evidence ( Insights - why this is the thing) |  | Backlog of research highlevel current state is understood and described.
[6 empty] | 🔹 Plan for next steps for the ‘project roadmap’ and ‘design discovery’ that likely describes: - Design brief/challenge - Design principles specific to context, audience. | 4) The current state is understood and described. | - detailed user experiences / sytems processes documented x2 - Topics of interests identified x2 - Quality documentation (Transcripts, bibliography, audio, video, photos) x2 - Surface pain points x2 - Identification of key user experiences and systems processes to map indepth x2 - Detailed user experiences / sytems processes documented - Problem context is well understood barriers/enablers (determinants) - Valididated assumptions - Interim assessment / analysis of data - Traceability of Pivot points |  |  |  | New understanding or learning about topic
[7 empty] | 5) A hypothesis has been defined and prioritised to explore within a Design Discovery | - New understanding/knowledge learnt 2 - Insights formed and evidenced x2 - Problem context is well understood barriers/enablers (determinants) - Valididated assumptions - Action Staement for next steps |  |  |  | A single "help me..." has been selected to explore with a Design Discovery.
The context in which the problem exists is understood. This includes at least "when", "where", "how often", and "likely barriers to adoption".
Defined problem areas, Deeper understanding of who is affected and when they occur.
Prioritisation of problems
Problem Definition
Resources required for ideation
Scope set for ideation and co-design (design for today vs 5 years - "future state")
Alignment with agency/lab goals and remit
Backlog of work
The foundation to create a Project Roadmap
The foundation to create a Design Brief
Research Discovery WIP | At the end of this discovery. Time will be taken to draw up a ‘Project Roadmap’. | Gate 4 Project Roadmap |  |  |  | A Project Roadmap The roadmap builds on the project scope document and details all the operational requirements to meet the outcomes defined and agreed in from the research discovery. | [6 empty] | https://drive.google.com/open?id=157p-nlpgfwTMsNJpFmG-KQfchX_P2os3ekO1taPrlLk
Design Discovery WIP | TBC | Gate 5 Design Brief |  | 🔸 Ideation 🔸 Sketches 🔸 Concepts 🔸 Trend research 🔸 Best practice 🔸 Information Archetecture 🔸 Workflows 🔸 Features List 🔸 Design Principles 🔸 Lateral examples 🔸 Repositories 🔸 Dependencies 🔸 front/back end management 🔸 Platforms 🔸 Services, hosting |  | A Design Brief Tangible concepts | Proof of exploration | [5 empty] | https://drive.google.com/open?id=12vi9_lp4xGv1D5h8frH7Q6vR5d_vBCsrNGp11PikjVQ
| TBC | Gate 6 Problem Definition |  | 🔸 Build / make stuff 🔸 Create wireframes 🔸 Explore tools - platform, mediums 🔸 Identifying what needs to be tested (Hypothesis) 🔸 Designing Workshops and Interviews for User-Testing 🔸 Preparing the Testing Environment 🔸 Concent forms + ethics 🔸 UI Wireframing 🔸 Design patterns 🔸 Feature mapping 🔸 Schematic flow diagrams 🔸 QA systems |  | A clearly defined design problem | [5 empty] | A clearly defined design problem | https://drive.google.com/open?id=1vXyTXFiQLDqGLlmFbDYe9C3tQt4VeNrEncnz1JpcFEY
| TBC | Gate 7 Problem Validation |  | 🔸 User-Testing Workshops / Interviews 🔸 Evaluating and synthesising user-testing results 🔸 Identifying Iterations 🔸 System integration testing 🔸 Function testing |  | A fully evidenced design problem: - Evidencing of the design approach to validate the problem space (ie UX research and validated learning) - The tests used to validate causal factors and identify potential (ie hypotheses developed and prioritised, validation plan for each hypothesis) - Validation conclusion for each hypothesis - Recommendation (ie continue or pivot) | [6 empty] | https://drive.google.com/open?id=1aqUvvpUtkrTGvBHZAAjd9auc1PT3nMCepKP9V1lgrkY
| TBC | Gate 8 Solution Validation |  | 🔸 Future service blueprint 🔸 Style tiles 🔸 Design Language 🔸 Functional Specifications |  | Validated Solutions that meet the needs of the Design problem 🔹 Solution Validation - Lo-fi testing and validation of the solutions proposed (UX) 🔹 Design brief 🔹 Inception deck and Lean canvas for all phases A brief recommendations paper at the end of problem definition, problem validation and solution validation (see note in decision requirements) 🔹 Blueprints 🔹 Technical user stories 🔹 Prototypes (lo-fi/interactive) 🔹 Visuals 🔹 Testing results 🔹 Product Owner and Process lead prepare a brief recommendations paper that describes: - Evidencing of the design approach that mitigates the problem space (Lo-fi testing and validation of the solutions proposed ie UX research) - Have a range of interventions been considered (ie Direct Intervention, Indirect Intervention, Policy Change, System Change, Process Change, Cross-Government) - Validation conclusion for the solution(s) - Recommendation (ie continue or pivot) | [5 empty] | A tested solution that has been validated with users on a small scale ✅ Solves the problem ✅ Enough exploration been done ✅ Enough development been done ✅ Enough testing been done ✅ Approval ✅ Presentation / Pitch / Document | https://drive.google.com/open?id=1Y-n9W3A2CG53Q3nE6-teRkIhlpfuLW4YqBsbokB7Lrs
Alpha | TBC | Gate 9 Product Definition Product definition is the beginning of the technology development process. These may also be reusable components. | 🔸 For agency(s) and lab team to have a clear understanding of what the MVP is and if its viable, desirable and feasible. | 🔸 Features are described in User Stories, and agreed by the team. The stories are owned by the Alpha champion. 🔸 understand if: - Hypothesis is true, MVP works as intended, MVP creates intended outcomes (this would require it to be live and running for a while) MVP creates unintended outcomes, Goals are realised. | 🔸 Technology prototypes are a tangible, testable working prototypes suitable to be put in front of the target audience | An MVP is defined 🔹 Development build sprints begin, and deliver new working features every 2 weeks 🔹 At the end of each sprint we decide if we do another sprint based on success in creating experimental features, time and budget, and deadlines in the problem domain 🔹 Design group verifies the alpha matches their design and if their design meets the needs they identified Evaluation report. The alpha may need to be allowed to run for some time. 🔹 MVP 🔹 Evaluation framework 🔹 Design roadmap 🔹 Design language 🔹 Runbook (pilot instructions/training) |  |  |  |  | Design group verifies the alpha matches their design and if their design meets the needs they identified |  | https://drive.google.com/open?id=1qEOKSOAO8E8YIYxfil39eefCcNvgfZ48ms6_XYFb1xg
Alpha | TBC | Gate 10 Product Validation | 🔸 Answer: Does the product fulfil the need? and impact the problem? outlined in the both the research and design discovery phases? 🔸 Manage expectations that this is all about the creation and testing of the MVP - manage expectation of what an MVP is and isn’t 🔸 Update SIRG and SWIG to ensure mandate is kept | [5 empty] | A product is validated against several criteria: Functionality ¦ Useability ¦ Scalability |  |  | ✅ Happy Clients ✅ Happy Users ✅ Functionality ✅ Polished "Shiny thing" | https://drive.google.com/open?id=17_X1jqiZyump064w0k-nXd7V1gsq59THm4C5rHRn5KA
Beta | On conclusion of product validation a full handover is set in motion | Gate 11 | 🔸 Handover - Where work that has reached DevOps status or requires further development outside of lab capacity/remit is transitioned over to a vendor or government agency. 🔸 For agency(s) and lab team to have a clear understanding of what the partnering and handover options are for the agency to take over the MVP and develop further. 🔸 Manage expectations of the work required to develop the service/product further 🔸 Update SIRG and SWIG to ensure mandate is kept 🔸 Reporting, storytelling and pitching benefits of the beta | Improving and developing the alpha by adding features and modifying based on evaluation and design roadmap. This will be done in partnership with the agencies and their technology partners. |  | 🔹 Both the project and the products that have emerged from the project are handed back to the relevant agency and /or a partnership with devOps team are build so that the product can be scaled and deployed outside of the lab environment through: Devops / Vendor partnering |  | A project plan, budget and people plan has been created which describes how the service will continue to evolve to meet user needs. There is a clear definition of how benefits will be measured, and how these will be monitored, and reported. This will include a baseline, and details of how the contribution your service makes to an overarching outcome or purpose will be publicly reported. Project and product/service risks have been identified, and managed throughout the phase. There is evidence that risks have been actively mitigated (including security vulnerabilities - see below). The solution has been designed and built with appropriate privacy and security safeguards and processes. The solution has been designed and built to be inclusive, ethical, and equitable. The solution uses open standards, common platforms, and generally works in the open. The solution manages data, including personal information, responsibly. | A service has been built which meets the demands of a live environment. This includes an understanding of how to build and scale the service while continuously making improvements to meet user needs. There must also be a commitment to fund the team required to do this on an ongoing basis. |  |  |  | https://drive.google.com/open?id=1z6qkUfwVJCHuf53lsT8dZqEBIsKtqWUeGDIauf4ap-w